TERMS OF REFERENCE

Terms of Reference for development of the training video for the census field staff on WG Questions set

- Context

The overall goal of the Okard Activity is to improve and sustain the independent living and functional ability of persons with disabilities, regardless of factors such as age, sex, or ethnicity, and their households in Lao PDR. One of the components of the Okard project is expected to contribute to improve the leadership and functioning of the National Committee for Persons with Disabilities (NCPD) in collecting disability-related data to implement disability-inclusive policies and programs.

Humanity & Inclusion (HI) is providing technical assistance to NCPD under the Okard project to collaborate with the Lao Statistics Bureau for the training of the 2025 Census field staff on administration of the WG short set of questions. With an objective to enhance the understanding of the census field staff on identifying functional difficulties of citizens at the household level and to administer the questions in accordance with the guidelines of the Washington Group, it is proposed to develop a training video to assist the field staff on the WG set of questions incorporated in the draft 2025 census questionnaire.

2. Description of the expected service:

2.1 General Objectives:

To develop the 20 minutes (2 videos of 10 minutes duration) which shows actors acting like enumerators and asking census questionnaires to identify the prevalence of disability.

2.2 Specific Objectives

To enhance the understanding of the census field staff on identifying functional difficulties of citizens at the household level and to administer the questions in accordance with the guidelines of the Washington Group.

2.3 Target group:

The video will be shown to the enumerators by the government as part of the census training.

  - Providing support from HI:

- HI will provide a full storyboard/ script in English /Lao and the concept of the video HI will provide a full the concept of the video;

- HI will coordinate with the consultant on the production based on the work plan;

- HI will facilitate the actors and actresses including people with disabilities;

- Provide feedback on the drafts production video.

- Sample a video spot produced by LSB will be shared to after signing a contract with HI;

  - Production team responsibilities

- Requested service: 20 minutes (2 videos of 10 minutes duration)

- Develop production plan;

- The producer needs to review, comment, and feedback on the storyboard/video script produced by HI;

- Providing the first draft of the video spot;

- Editing/making graphic video;

- Insert voice in the video;

- Include Lao sub-titles

- Deliver the final video by the expected deadline mentioned below.

3. Required Consultant profile:

- HI is looking for individual consultant or a firm with qualifications and experience, to produce a video spot as requested in this ToR;

- Must be a legal entity;

- Experience in similar work is desirable;

4. Duration and place of performance of services

The duration of the consultant should be between 29th April to 16th May 2024. The filming should be conducted in Vientiane Capital.

5. Work Plan

| Deliverables/ Outputs | Timeframe | Review and Approvals Required |
| --- | --- | --- |
| Preparation work (story board, script, … | 29th April – 16th May 2024 | Producer, HI and the technical working group |
| Conduct Filming |  | Producer, HI and the technical working group |
| 1st version of the module 01 and 02 video |  | HI and the technical working group |
| 2nd final version |  | HI and the technical working group |
| Testing of the training video during the pilot census around |  | HI and the technical working group |
| Comment to the prefinal version |  | HI and the technical working group |
| Final hand over of the training video around |  | HI and the technical working group |

6. Delivery Product

- A video comprising two modules with a total duration of 10 minutes developed

- A quality of the video should be at least full HD (1920x1080) pixels

- The videos (module 01 and 02) are developed in Lao language with sub-titles in Lao as suggested by the technical working group.

- The consultant/agency presented the work to the technical working group including NCPD when requested during the contract period

- Final handover of the training video around 24th May 2024

7. Contact person:

The Consultant shall refer any questions regarding the internal organisation of HI and the services to be provided to Khomvanh SAYARATH, OKARD Project Manager, Email: k.sayarath@hi.org who shall alone be empowered to make any changes to the services described above by way of a rider to this Contract signed by both parties.

- Financial proposal:

Submitted financial offer must include professional service fee including, production cost, travel, accommodation, perdiem cost, any applicable tax (withholding tax or VAT..).., etc.

- Required document for submission the proposal:

Interested service providers, please submit your application as follow:

- a cover letter / motivation letter

- the proposed technical proposal including the work plan and budget plan

- Some samples of Videos

- EVALUATION PROCEDURE

Evaluation of the expression of interest will be made through a selection committee in two phases:

1.	Administrative selection: The committee will first check for completeness of the application and verify that all compulsory items listed above are included. Incomplete applications will not be considered for technical selection.

2.	Technical selection: The best application will be selected based on the quality of the technical proposal, the competitiveness of the financial proposal, the skills and previous experiences of the consultant, and the demonstrated expertise of the applicant to successfully undertake the assignment.

Only candidates who pass the administrative selection will be considered for the technical assessment. Shortlisted applicants may be invited for an online interview (or offline interview).

HI reserves the right to contact the applicants for additional information or clarification before the final selection by the selection committee. After interview only the selected candidate will be contacted.

- DEADLINE FOR SUBMISSION

The deadline for the submission of the application is not later than 18 April 2024, to the e-mail address procurement@laos.hi.org

Applications submitted after the deadline will not be considered.

Only shortlisted candidates will be contacted. Selected applicants may be invited for an interview or discussion.